## Abstract Timeline old (hidden)
Quantitative Analysis- already underway at SCHARP
Conference | Dates | Location | Abstract deadline | abstract to MTN MRC | abstract to Sponsor (if other than DAIDS) | abstract to PPC | Data request to SCHARP for analysis already underway* | Concept submission to PPC if data analysis is already underway in this area
CROI late-breaker | Feb 13-16 | Seattle | 2017-01-03 | 2016-12-20 | 2016-12-13 | 2016-12-06 | 2016-11-08 | 2016-10-25
SA AIDS | Jun 13-16 | Durban | 2017-01-06 | 2016-12-23 | 2016-12-16 | 2016-12-09 | 2016-11-11 | 2016-10-28
ICMI 2017 | Jun 19-21 | Philadelphia | 2017-02-17 | 2017-02-03 | 2017-01-27 | 2017-01-20 | 2016-12-23 | 2016-12-09
IAPAC Adherence 2017 | Jun 4-6 | Miami | 2017-02-24 | 2017-02-10 | 2017-02-03 | 2017-01-27 | 2016-12-30 | 2016-12-16
IAPAC 2017 Late-breaker | Jun 4-6 | Miami | 2017-04-10 | 2017-03-27 | 2017-03-20 | 2017-03-13 | 2017-02-13 | 2017-01-30
ISSTDR | July 9-12 | Rio | 2016-12-15 | 2016-12-01 | 2016-11-24 | 2016-11-17 | 2016-10-20 | 2016-10-06
IAS 2017 | July 23-26 | Paris | 2017-01-25 | 2017-01-11 | 2017-01-04 | 2016-12-23 | 2016-11-20 | 2016-11-06
IAS 2017 late-breaker | July 23-26 | Paris | 2017-05-15 | 2017-05-01 | 2017-04-24 | 2017-04-12 | 2017-03-10 | 2017-02-24
IDSOG 2017 | Aug 10-12 | Park City, UT | 2017-04-24 | 2017-04-10 | 2017-04-03 | 2017-03-22 | 2017-02-17 | 2017-02-03
*For analyses that are already ongoing, it is helpful if investigators let SCHARP know as early as possible which conference they are planning to submit to. At a minimum, SCHARP requests 4 weeks notice for analyses that are already underway. The minimum amount of time may vary, depending on the anticipated number of abstracts for a specific meeting.
Quantitative Analysis- new data request to SCHARP- 6 wks in advance
Conference | Dates | Location | Abstract deadline | abstract to MTN MRC | abstract to Sponsor (if other than DAIDS) | abstract to PPC | new data request to SCHARP- 6 wks in adv. | Concept submission to PPC if new data request
CROI late-breaker | Feb 13-16 | Seattle | 2017-01-03 | 2016-12-20 | 2016-12-13 | 2016-12-06 | 2016-10-25 | 2016-10-11
SA AIDS | Jun 13-16 | Durban | 2017-01-06 | 2016-12-23 | 2016-12-16 | 2016-12-09 | 2016-10-28 | 2016-10-21
ICMI 2017 | Jun 19-21 | Philadelphia | 2017-02-17 | 2017-02-03 | 2017-01-27 | 2017-01-20 | 2016-12-23 | 2016-12-09
IAPAC Adherence 2017 | Jun 4-6 | Miami | 2017-02-24 | 2017-02-10 | 2017-02-03 | 2017-01-27 | 2016-12-30 | 2016-12-16
IAPAC 2017 Late-breaker | Jun 4-6 | Miami | 2017-04-10 | 2017-03-27 | 2017-03-20 | 2017-03-13 | 2017-02-13 | 2017-01-30
ISSTDR | July 9-12 | Rio | 2016-12-15 | 2016-12-01 | 2016-11-24 | 2016-11-17 | 2016-10-06 | 2016-09-22
IAS 2017 | July 23-26 | Paris | 2017-01-25 | 2017-01-11 | 2017-01-04 | 2016-12-23 | 2016-11-20 | 2016-11-06
IAS 2017 late-breaker | July 23-26 | Paris | 2017-05-15 | 2017-05-01 | 2017-04-24 | 2017-04-12 | 2017-03-10 | 2017-02-24
IDSOG 2017 | Aug 10-12 | Park City, UT | 2017-04-24 | 2017-04-10 | 2017-04-03 | 2017-03-22 | 2017-02-17 | 2017-02-03
Descriptive Analyses (SCHARP data request not required)
Conference | Dates | Location | Abstract deadline | abstract to MTN MRC | abstract to Sponsor (if other than DAIDS) | abstract to PPC | Concept submission to PPC
CROI late-breaker | Feb 13-16 | Seattle | 2017-01-03 | 2016-12-20 | 2016-12-13 | 2016-12-06 | 2016-11-06
SA AIDS | Jun 13-16 | Durban | 2017-01-06 | 2016-12-23 | 2016-12-16 | 2016-12-09 | 2016-11-09
ICMI 2017 | Jun 19-21 | Philadelphia | 2017-02-17 | 2017-02-03 | 2017-01-27 | 2017-01-20 | 2016-12-23
IAPAC Adherence 2017 | Jun 4-6 | Miami | 2017-02-24 | 2017-02-10 | 2017-02-03 | 2017-01-27 | 2016-12-30
IAPAC 2017 Late-breaker | Jun 4-6 | Miami | 2017-04-10 | 2017-03-27 | 2017-03-20 | 2017-03-13 | 2017-02-13
ISSTDR | July 9-12 | Rio | 2016-12-15 | 2016-12-01 | 2016-11-24 | 2016-11-17 | 2016-10-18
IAS 2017 | July 23-26 | Paris | 2017-01-25 | 2017-01-11 | 2017-01-04 | 2016-12-23 | 2016-11-20
IAS 2017 late-breaker | July 23-26 | Paris | 2017-05-15 | 2017-05-01 | 2017-04-24 | 2017-04-12 | 2017-03-10
IDSOG 2017 | Aug 10-12 | Park City, UT | 2017-04-24 | 2017-04-10 | 2017-04-03 | 2017-03-22 | 2017-02-17
Formulas:
abstract to MTN MRC = [Abstract deadline]-14
Concept submission to PPC = [abstract to PPC]-30

## Concept-Abstract Timeline
<-------------------<<-------------------<<-------------------<<-------------------<<-------------------<<-------------------<<----------------Deadlines Read from Right to Left
**DATES IN RED ARE ESTIMATED -- THESE WILL BE UPDATED WHEN ACTUAL SUBMISSION DEADLINES ARE AVAILABLE FROM THE CONFERENCE ORGANIZERS.
Quantitative Analysis- NEW Data request to SCHARP
Conference | Dates | Location | Abstract Deadline | Abstract to MTN MRC | Abstract to Sponsor (if other than DAIDS) | Abstract to PPC | NEW Data request to SCHARP- 6 Wks in Advance | Concept submission to PPC (if new data request)
CROI 2022 | Feb 13-16, 2022 | Denver, CO | 2021-11-01 | 2021-10-25 | 2021-10-18 | 2021-10-13 | 2021-09-01 | 2021-08-25
CROI 2022 LB | Feb 13-16, 2022 | Denver, CO | 2022-01-05 | 2021-12-29 | 2021-12-22 | 2021-12-17 | 2021-11-05 | 2021-10-29
AIDS 2022 | 29 July - 2 Aug 2022 | Montreal, Canada/Virtual | 2022-01-27 | 2022-01-20 | 2022-01-13 | 2022-01-08 | 2021-11-27 | 2021-11-20
AIDS 2022 LB | 29 July - 2 Aug 2022 | Montreal, Canada/Virtual | 2022-05-10 | 2022-05-03 | 2022-04-26 | 2022-04-21 | 2022-03-10 | 2022-03-03
Infectious Diseases Society for Obstetrics and Gynecology | 4-6 August 2022 | Boston, MA | TBD
Adherence 2022 | TBD | TBD | TBD
HIV R4P 2023 | TBD | TBD | TBD
Quantitative Analysis- Analysis already underway at SCHARP
Conference | Dates | Location | Abstract Deadline | Abstract to MTN MRC | Abstract to Sponsor (if other than DAIDS) | Abstract to PPC | Data request to SCHARP for analysis already underway* | Concept submission to PPC (if data analysis is already underway in this area)
CROI 2022 | Feb 13-16, 2022 | Denver, CO | 2021-11-01 | 2021-10-25 | 2021-10-18 | 2021-10-13 | 2021-09-10 | 2021-09-03
CROI 2022 LB | Feb 13-16, 2022 | Denver, CO | 2022-01-05 | 2021-12-29 | 2021-12-22 | 2021-12-17 | 2021-11-14 | 2021-11-07
AIDS 2022 | 29 July - 2 Aug 2022 | Montreal, Canada/Virtual | 2022-01-27 | 2022-01-20 | 2022-01-13 | 2022-01-08 | 2021-12-06 | 2021-11-29
AIDS 2022 LB | 29 July - 2 Aug 2022 | Montreal, Canada/Virtual | 2022-05-10 | 2022-05-03 | 2022-04-26 | 2022-04-21 | 2022-03-19 | 2022-03-12
Infectious Diseases Society for Obstetrics and Gynecology | 4-6 August 2022 | Boston, MA | TBD
Adherence 2022 | TBD | TBD | TBD
HIV R4P 2023 | TBD | TBD | TBD
*For analyses that are already ongoing, it is helpful if investigators let SCHARP know as early as possible which conference they are planning to submit to. At a minimum, SCHARP requests 4 weeks notice for analyses that are already underway. The minimum amount of time may vary, depending on the anticipated number of abstracts for a specific meeting.
Descriptive Analyses (SCHARP data request not required)
Conference | Dates | Location | Abstract Deadline | Abstract to MTN MRC | Abstract to Sponsor (if other than DAIDS) | Abstract to PPC | Concept submission to PPC
CROI 2022 | Feb 13-16, 2022 | Denver, CO | 2021-11-01 | 2021-10-25 | 2021-10-18 | 2021-10-13 | 2021-09-10
CROI 2022 LB | Feb 13-16, 2022 | Denver, CO | 2022-01-05 | 2021-12-29 | 2021-12-22 | 2021-12-17 | 2021-11-14
AIDS 2022 | 29 July - 2 Aug 2022 | Montreal, Canada/Virtual | 2022-01-27 | 2022-01-20 | 2022-01-13 | 2022-01-08 | 2021-12-06
AIDS 2022 LB | 29 July - 2 Aug 2022 | Montreal, Canada/Virtual | 2022-05-10 | 2022-05-03 | 2022-04-26 | 2022-04-21 | 2022-03-19
Infectious Diseases Society for Obstetrics and Gynecology | 4-6 August 2022 | Boston, MA | TBD
Adherence 2022 | TBD | TBD | TBD
HIV R4P 2023 | TBD | TBD | TBD
Formulas:
Abstract to MTN MRC = [TBD]-7
Concept submission to PPC = [Abstract to PPC]-33

## Oral-Poster Timeline
<-------------------<<-------------------<<-------------------<<-------------------<<-------------------<<--------------------Deadlines Read from Right to Left
Oral/Poster Presentation Review Timeline
Conference | Dates | Location | Presentation Deadline | Submit to MTN MRC | Submit to Sponsor (if other than DAIDS) | Author Start (submit draft to co-authors)
CROI 2022 | Feb 13-16, 2022 | Denver, CO | 2022-02-12 | 2022-02-07 | 2022-01-31 | 2022-01-21
CROI 2022 LB | Feb 13-16, 2022 | Denver, CO | 2022-02-12 | 2022-02-07 | 2022-01-31 | 2022-01-21
AIDS 2022 | 29 July - 2 Aug 2022 | Montreal, Canada/Virtual | 2022-07-01 | 2022-06-26 | 2022-06-19 | 2022-06-09
AIDS 2022 LB | 29 July - 2 Aug 2022 | Montreal, Canada/Virtual | 2022-07-15 | 2022-07-10 | 2022-07-03 | 2022-06-23
Infectious Diseases Society for Obstetrics and Gynecology | 4-6 August 2022 | Boston, MA | TBD
Adherence 2022 | TBD
HIV R4P 2023 | TBD
Formulas:
Submit to MTN MRC = [Presentation Deadline]-5
Submit to Sponsor (if other than DAIDS) = [Submit to MTN MRC]-7
Note on E6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimated! Virtual conferences tend to want these about a month in advance.
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimated!