## Abstract Timeline old (hidden)
Quantitative Analysis- already underway at SCHARP
Conference | Dates | Location | Abstract deadline | abstract to MTN MRC | abstract to Sponsor (if other than DAIDS) | abstract to PPC | Data request to SCHARP for analysis already underway* | Concept submission to PPC if data analysis is already underway in this area
CROI late-breaker | Feb 13-16 | Seattle | 2017-01-03 | 2016-12-20 | 2016-12-13 | 2016-12-06 | 2016-11-08 | 2016-10-25
SA AIDS | Jun 13-16 | Durban | 2017-01-06 | 2016-12-23 | 2016-12-16 | 2016-12-09 | 2016-11-11 | 2016-10-28
ICMI 2017 | Jun 19-21 | Philadelphia | 2017-02-17 | 2017-02-03 | 2017-01-27 | 2017-01-20 | 2016-12-23 | 2016-12-09
IAPAC Adherence 2017 | Jun 4-6 | Miami | 2017-02-24 | 2017-02-10 | 2017-02-03 | 2017-01-27 | 2016-12-30 | 2016-12-16
IAPAC 2017 Late-breaker | Jun 4-6 | Miami | 2017-04-10 | 2017-03-27 | 2017-03-20 | 2017-03-13 | 2017-02-13 | 2017-01-30
ISSTDR | July 9-12 | Rio | 2016-12-15 | 2016-12-01 | 2016-11-24 | 2016-11-17 | 2016-10-20 | 2016-10-06
IAS 2017 | July 23-26 | Paris | 2017-01-25 | 2017-01-11 | 2017-01-04 | 2016-12-23 | 2016-11-20 | 2016-11-06
IAS 2017 late-breaker | July 23-26 | Paris | 2017-05-15 | 2017-05-01 | 2017-04-24 | 2017-04-12 | 2017-03-10 | 2017-02-24
IDSOG 2017 | Aug 10-12 | Park City, UT | 2017-04-24 | 2017-04-10 | 2017-04-03 | 2017-03-22 | 2017-02-17 | 2017-02-03
*For analyses that are already ongoing, it is helpful if investigators let SCHARP know as early as possible which conference they are planning to submit to. At a minimum, SCHARP requests 4 weeks notice for analyses that are already underway. The minimum amount of time may vary, depending on the anticipated number of abstracts for a specific meeting.
Quantitative Analysis- new data request to SCHARP- 6 wks in advance
Conference | Dates | Location | Abstract deadline | abstract to MTN MRC | abstract to Sponsor (if other than DAIDS) | abstract to PPC | new data request to SCHARP- 6 wks in adv. | Concept submission to PPC if new data request
CROI late-breaker | Feb 13-16 | Seattle | 2017-01-03 | 2016-12-20 | 2016-12-13 | 2016-12-06 | 2016-10-25 | 2016-10-11
SA AIDS | Jun 13-16 | Durban | 2017-01-06 | 2016-12-23 | 2016-12-16 | 2016-12-09 | 2016-10-28 | 2016-10-21
ICMI 2017 | Jun 19-21 | Philadelphia | 2017-02-17 | 2017-02-03 | 2017-01-27 | 2017-01-20 | 2016-12-23 | 2016-12-09
IAPAC Adherence 2017 | Jun 4-6 | Miami | 2017-02-24 | 2017-02-10 | 2017-02-03 | 2017-01-27 | 2016-12-30 | 2016-12-16
IAPAC 2017 Late-breaker | Jun 4-6 | Miami | 2017-04-10 | 2017-03-27 | 2017-03-20 | 2017-03-13 | 2017-02-13 | 2017-01-30
ISSTDR | July 9-12 | Rio | 2016-12-15 | 2016-12-01 | 2016-11-24 | 2016-11-17 | 2016-10-06 | 2016-09-22
IAS 2017 | July 23-26 | Paris | 2017-01-25 | 2017-01-11 | 2017-01-04 | 2016-12-23 | 2016-11-20 | 2016-11-06
IAS 2017 late-breaker | July 23-26 | Paris | 2017-05-15 | 2017-05-01 | 2017-04-24 | 2017-04-12 | 2017-03-10 | 2017-02-24
IDSOG 2017 | Aug 10-12 | Park City, UT | 2017-04-24 | 2017-04-10 | 2017-04-03 | 2017-03-22 | 2017-02-17 | 2017-02-03
Descriptive Analyses (SCHARP data request not required)
Conference | Dates | Location | Abstract deadline | abstract to MTN MRC | abstract to Sponsor (if other than DAIDS) | abstract to PPC | Concept submission to PPC
CROI late-breaker | Feb 13-16 | Seattle | 2017-01-03 | 2016-12-20 | 2016-12-13 | 2016-12-06 | 2016-11-06
SA AIDS | Jun 13-16 | Durban | 2017-01-06 | 2016-12-23 | 2016-12-16 | 2016-12-09 | 2016-11-09
ICMI 2017 | Jun 19-21 | Philadelphia | 2017-02-17 | 2017-02-03 | 2017-01-27 | 2017-01-20 | 2016-12-23
IAPAC Adherence 2017 | Jun 4-6 | Miami | 2017-02-24 | 2017-02-10 | 2017-02-03 | 2017-01-27 | 2016-12-30
IAPAC 2017 Late-breaker | Jun 4-6 | Miami | 2017-04-10 | 2017-03-27 | 2017-03-20 | 2017-03-13 | 2017-02-13
ISSTDR | July 9-12 | Rio | 2016-12-15 | 2016-12-01 | 2016-11-24 | 2016-11-17 | 2016-10-18
IAS 2017 | July 23-26 | Paris | 2017-01-25 | 2017-01-11 | 2017-01-04 | 2016-12-23 | 2016-11-20
IAS 2017 late-breaker | July 23-26 | Paris | 2017-05-15 | 2017-05-01 | 2017-04-24 | 2017-04-12 | 2017-03-10
IDSOG 2017 | Aug 10-12 | Park City, UT | 2017-04-24 | 2017-04-10 | 2017-04-03 | 2017-03-22 | 2017-02-17
Formulas:
abstract to MTN MRC = [Abstract deadline]-14
Concept submission to PPC = [abstract to PPC]-30

## Concept-Abstract Timeline
<-------------------<<-------------------<<-------------------<<-------------------<<-------------------<<-------------------<<----------------Deadlines Read from Right to Left
**DATES IN RED ARE ESTIMATED -- THESE WILL BE UPDATED WHEN ACTUAL SUBMISSION DEADLINES ARE AVAILABLE FROM THE CONFERENCE ORGANIZERS.
Quantitative Analysis- NEW Data request to SCHARP
Conference | Dates | Location | Abstract Deadline | Abstract to MTN MRC | Abstract to Sponsor (if other than DAIDS) | Abstract to PPC | NEW Data request to SCHARP- 6 Wks in Advance | Concept submission to PPC (if new data request)
IDSOG 2020 | Aug 13-15 | Boston | 2020-04-06 | 2020-03-23 | 2020-03-16 | 2020-03-09 | 2020-01-27 | 2020-01-13
APHA 2020 | Oct 24-28 | San Francisco | 2020-02-20 | 2020-02-06 | 2020-01-30 | 2020-01-23 | 2019-12-12 | 2019-11-28
AIDS/IAS 2020 | Jul 6-10 | Oakland | 2020-01-14 | 2019-12-31 | 2019-12-24 | 2019-12-17 | 2019-11-05 | 2019-10-22
AIDS/IAS 2020 LB | Jul 6-10 | Oakland | 2020-04-15 | 2020-04-01 | 2020-03-25 | 2020-03-18 | 2020-02-05 | 2020-01-22
HIVR4P 2020 | Oct 11-15 | Cape Town | 2020-04-23 | 2020-04-02 | 2020-03-26 | 2020-03-19 | 2020-02-06 | 2020-01-23
HIVR4P 2020 LB | Oct 11-15 | Cape Town | 2020-08-05 | 2020-07-15 | 2020-07-08 | 2020-07-01 | 2020-05-20 | 2020-05-06
Quantitative Analysis- Analysis already underway at SCHARP
Conference | Dates | Location | Abstract Deadline | Abstract to MTN MRC | Abstract to Sponsor (if other than DAIDS) | Abstract to PPC | Data request to SCHARP for analysis already underway* | Concept submission to PPC (if data analysis is already underway in this area)
IDSOG 2020 | Aug 13-15 | Boston | 2020-04-06 | 2020-03-23 | 2020-03-16 | 2020-03-04 | 2020-01-31 | 2020-01-17
APHA 2020 | Oct 24-28 | San Francisco | 2020-02-20 | 2020-02-06 | 2020-01-30 | 2020-01-18 | 2019-12-16 | 2019-12-02
AIDS/IAS 2020 | Jul 6-10 | Oakland | 2020-01-14 | 2019-12-31 | 2019-12-24 | 2019-12-12 | 2019-11-09 | 2019-10-26
AIDS/IAS 2020 LB | Jul 6-10 | Oakland | 2020-04-15 | 2020-04-01 | 2020-03-25 | 2020-03-13 | 2020-02-09 | 2020-01-26
HIVR4P 2020 | Oct 11-15 | Cape Town | 2020-04-23 | 2020-04-02 | 2020-03-26 | 2020-03-14 | 2020-02-10 | 2020-01-27
HIVR4P 2020 LB | Oct 11-15 | Cape Town | 2020-08-05 | 2020-07-15 | 2020-07-08 | 2020-06-26 | 2020-05-24 | 2020-05-10
*For analyses that are already ongoing, it is helpful if investigators let SCHARP know as early as possible which conference they are planning to submit to. At a minimum, SCHARP requests 4 weeks notice for analyses that are already underway. The minimum amount of time may vary, depending on the anticipated number of abstracts for a specific meeting.
Descriptive Analyses (SCHARP data request not required)
Conference | Dates | Location | Abstract Deadline | Abstract to MTN MRC | Abstract to Sponsor (if other than DAIDS) | Abstract to PPC | Concept submission to PPC
IDSOG 2020 | Aug 13-15 | Boston | 2020-04-06 | 2020-03-23 | 2020-03-16 | 2020-03-04 | 2020-01-31
APHA 2020 | Oct 24-28 | San Francisco | 2020-02-20 | 2020-02-06 | 2020-01-30 | 2020-01-18 | 2019-12-16
AIDS/IAS 2020 | Jul 6-10 | Oakland | 2020-01-15 | 2020-01-01 | 2019-12-25 | 2019-12-13 | 2019-11-10
AIDS/IAS 2020 LB | Jul 6-10 | Oakland | 2020-04-15 | 2020-04-01 | 2020-03-25 | 2020-03-13 | 2020-02-09
HIVR4P 2020 | Oct 11-15 | Cape Town | 2020-04-23 | 2020-04-02 | 2020-03-26 | 2020-03-14 | 2020-02-10
HIVR4P 2020 LB | Oct 11-15 | Cape Town | 2020-08-05 | 2020-07-15 | 2020-07-08 | 2020-06-26 | 2020-05-24
Formulas:
Abstract to MTN MRC = [Abstract Deadline]-14
Concept submission to PPC = [Abstract to PPC]-33

## Oral-Poster Timeline
<-------------------<<-------------------<<-------------------<<-------------------<<-------------------<<--------------------Deadlines Read from Right to Left
Oral/Poster Presentation Review Timeline
Conference | Dates | Location | Presentation Deadline | Submit to MTN MRC | Submit to Sponsor (if other than DAIDS) | Submit to PPC | Author Start (submit draft to co-authors)
IDSOG 2020 | Aug 13-15 | Boston | 2020-08-13 | 2020-08-03 | 2020-07-27 | 2020-07-20 | 2020-07-06
APHA 2020 | Oct 24-28 | San Francisco | 2020-10-24 | 2020-10-14 | 2020-10-07 | 2020-09-30 | 2020-09-16
AIDS/IAS 2020 | Jul 6-10 | Oakland | 2020-07-06 | 2020-06-26 | 2020-06-19 | 2020-06-12 | 2020-05-29
HIVR4P 2020 | Oct 11-15 | Cape Town | 2020-10-11 | 2020-10-01 | 2020-09-24 | 2020-09-17 | 2020-09-03
Formulas:
Submit to MTN MRC = [Presentation Deadline]-10
Submit to Sponsor (if other than DAIDS) = [Submit to MTN MRC]-7
Submit to PPC = [Submit to Sponsor (if other than DAIDS)]-7